## Sheet1
Task | Start Date | Duration
Read About Restaurant and interview | 2020-03-03 | 7
Problem Identify | 2020-03-05 | 5
Collection Requirement | 2020-03-08 | 3
Analysis System | 2020-03-12 | 10
Make Proposal | 2020-03-20 | 3
Designing the Recommanded System | 2020-03-24 | 15
installation and commissioning of hardware | 2020-04-06 | 5
programming for system | 2020-04-11 | 45
Testing the system | 2020-05-26 | 5
implement and evaluate the system | 2020-06-02 | 5